| Action | Category | HPAC Recommendation | 2020 Budget | Start | End |
| --- | --- | --- | --- | --- | --- |
| Emergency Shelter and Transitional Housing with Services | Housing | Establish Temporary-Housing in a permanent facility to serve Monroe residents with adjacent secured parking for those living in vehicles and RVs for overnight stay | $50,000 | 1/2020 | 12/2020 |
| Evaluate Properties |  |  |  | 5/2020 | 12/2020 |
| Negotiate Lease |  |  |  | 6/2020 | 12/2020 |
| Write RFP and secure Program Manager through RFP |  |  |  | 4/2020 | 12/2020 |
| Develop criteria with Technical Advisory Committee (TAC) Provide Rental Assistance through RFP |  |  | $46,000 (HB1406) | 1/2020 | 12/2020 |
| Establish Sky Valley Housing Consortium | Housing | Establish Sky Valley Housing Consortium to establish short, long-term and alternative housing Increase alternative housing that includes but is not limited to men, youth, LGBTQ, families and pets |  | 1/2020 | 12/2020 |
| Inventory surplus property Identify housing needs Work with Technical Advisory Committee to identify partners and available funding |  |  |  | 5/2020 1/2020 02/2020 | 12/2020 06/2020 06/2020 |
| Form a Technical Advisory Committee | Partners | Establish Service Provider Networks to provide services and housing 24/7 in Sky Valley Involve other public entities in a network to prevent and end homelessness in Sky Valley |  | 1/2020 | 12/2020 |
| Identify non-profit stakeholders and partners |  |  |  | 1/2020 | 3/2020 |
| Determine shared mission and vision |  |  |  | 2/2020 | 4/2020 |
| Evaluate needs and resources for one-stop shop |  |  |  | 3/2020 | 5/2020 |
| Write scope of work for Request for Proposal for one-stop shop |  |  |  | 4/2020 | 6/2020 |
| Establish Transportation service between Sky Valley and Everett | Partners | Increase public transportation between Monroe & Everett |  | 1/2020 | 12/2020 |
| Evaluate transportation needs with partners |  |  |  | 1/2020 | 3/2020 |
| Evaluate existing transportation contracts with non-profits (e.g. Senior Center; SVT) |  |  |  | 1/2020 | 3/2020 |
| Apply for Community Transit GO (grant) program |  |  |  | 3/2020 | 6/2020 |
| Provide information about services to remain housed, financial training, and incentives for businesses to hire employees with entry level skills, information about mental and behavioral health services. | Partners | Create an education campaign that supports affordable housing, job training, and treatment options |  | 1/2020 | 12/2020 |
| Work with partners to develop and promote annual “human service days” set up like a vendor show |  |  |  |  |  |
| Educational Campaign (Enviroissues Contract) | Prevention | Create an education campaign about homelessness: causes, prevention strategies, and alternatives | $50,000 (Budgeted) | 1/2020 | 12/2020 |
| Develop education and outreach communication plan |  |  |  | 12/2019 | 12/2020 |
| Educate property owners about laws, enforcement, trespass - Chamber of Commerce & Downtown Monroe Association |  |  |  | 2/2020 | 12/2020 |
| Educate public about aggressive panhandling, property crime, and personal safety. |  |  |  | 2/2020 | 12/2020 |
| Educate public about safety regarding vigilantism and bullying |  |  |  | 2/2020 | 12/2020 |
| Develop and implement Block Watch Program - residential and business buy in/education/communication - training & certification program. |  |  |  | 10/2020 | 12/2020 |
| Develop working relationship with McKinney Vento liaisons at Monroe School District | Prevention | Promote social service networks focused on youth and families |  | 3/2020 | 12/2020 |
| Identify needs of homeless families | Prevention | Gather and analyze accurate data about homelessness in Monroe |  | 10/2020 | 3/2020 |
| Work with McKinney-Vento Family Liaisons in the Monroe School District to distribute flyers of local and county services for homeless students and families and encourage MSC to post flyers on school premises. |  |  |  | 3/2020 | 6/2020 |
| Define 2021 Work Plan, Priorities, and Implementation Model | Prevention/ Policy & Budget | Adopt and fund a Six-Year Plan to fulfill HPAC’s recommendations |  | 6/2020 | 12/2020 |
| Implement law enforcement strategies | Public Safety | Implement law enforcement strategies and regulations that increase personal accountability and adhere to civil and personal rights |  | 1/2020 | 12/2020 |
| Review Solicitation Regulations |  |  |  | 2/2020 | 4/2020 |
| Evaluate bail fees |  |  |  | 4/2020 | 9/2020 |
| Develop and implement Block Watch Program - residential and business buy in/education/communication - training & certification program. |  | Initiate a residential and business crime prevention program |  | 10/2020 | 12/2020 |
| Continue Embedded Social Worker Program | Public Safety | Continue to budget for embedded social worker/community outreach team |  | 1/2020 | 12/2020 |
| Police Department (Existing program) |  |  | $73,000 |  |  |
| Public Defender (New level of services) |  |  | $20,000 | 3/2020 | 12/2020 |
| Install Cameras in parks |  | Use technology for public safety and to protect infrastructure. | $17,000 | 1/2020 | 6/2020 |
| Collect data on court cases. Determine with Monroe Municipal Court the costs/benefits of community court model | Public Safety | Implement Community Court so treatment for addiction and mental health can be offered as an alternative to jail Gather and analyze data about crime in Monroe |  | 6/2020 | 12/2021 |
| Identify partners to develop community court model |  |  |  |  |  |
| Determine with Monroe Municipal Court and partners the costs/benefits of community court model |  |  |  | 1/2021 | 12/2021 |
| Coordinated Services – One Stop Shop | Support Services | Create a coordinated homeless response center Create a system of services that responds to the homeless crisis 24/7 Establish more accessible mental health and addiction services in Monroe | $50,000 | 4/2020 | 12/2020 |
| Develop scope of work with Technical Advisory Committee |  |  |  | 1/2020 | 5/2020 |
| Issue Request for Proposal (RFP) |  |  |  | 3/2020 | 6/2020 |
| Award RFPs |  |  |  | 6/2020 | 7/2020 |
| Establish Homeless HMIS/By name lists |  |  |  | 6/2020 | 12/2020 |
| Work with Technical Advisory Committee and Snohomish County to identify resources to provide housing and mental health navigators in the Sky Valley | Support Services | Obtain supportive services to navigate people through resources |  | 1/2020 | 12/2020 |
| Provide facilities and funding for non-profits |  | Support agencies that serve ad promote self-reliance |  | On-going |  |
| Work with Take the Next Step and Volunteers of America to designate a family resource center and/or services in Monroe |  |  |  | 3/2020 | 12/2020 |
| Identify performance measures, such as reduction in the number of homeless individuals; reduction in lengths of stays at emergency shelters; increase in rental vacancy rate; and a full Homeless Management Information (HMIS) utilized by service providers. | Policy & Budget | Create a Six-year Plan, which includes performance measures |  | 6/2020 | 9/2020 |
| Lobbing for changes to State and Federal law | Policy & Budget | Lobby legislators at all levels to increase funding for addiction and mental health treatment, affordable housing, job training, and support services Identify and lobby for new law enforcement strategies focused on personal accountability of homeless |  | 1/2020 | 12/2020 |
| Collaborate with Affordable Housing Consortium (AHC) on writing new housing chapter for the city’s comprehensive plan update. | Policy & Budget | Engage developers in building affordable and subsidized housing |  | 6/2020 | 12/2020 |
| Continue HPAC as a standing committee |  |  |  |  |  |
|  | Policy & Budget | Implement HB 1406 and explore all revenue options for housing, mental health, and chemical dependency. |  | 7/2019 | 3/2021 |
| Identify needs |  |  | $46,000 (HB1406) | 4/2020 | 9/2020 |
| Develop criteria with Technical Advisory Committee (TAC) |  |  |  | 9/2020 | 12/2020 |
| Provide Rental Assistance through RFP |  |  |  | 12/2020 | 12/2021 |
| Evaluate program |  |  |  | 6/2020 | 12/2020 |
|  |  | Continue HPAC as a standing Committee |  |  |  |
| Define 2021 Work Plan, Priorities, and Implementation Model | Policy & Budget | Adopt and fund a Six-Year Plan to fulfill HPAC’s recommendations |  | 6/2020 | 12/2020 |

Total 2020 Investment $312,000